SMART CLINIC

Multi-Clinic Management SaaS

Implementation and Quality Plan

Version 1.1  |  Baseline candidate (revision B)

26 October 2026 (revision B)

Document ID: SC-PLAN-001  |  Sources: SRS v1.1 rev B, Technical Architecture v1.1 rev B

Five development gates for Claude Code Cloud Sessions within a USD 35 total allocation (planning caps). No application code. All example data is fictional.

Table of Contents

1. Document Control	4

1.1 Revision History	4

1.2 Approval	4

2. Purpose, Inputs and Scope	5

3. Delivery Strategy	6

3.1 Gate Overview	6

3.2 Gate Sequence and Dependencies	6

3.3 Gate Lifecycle	6

4. Claude Code Cloud Operating Rules (Budget Discipline)	7

4.1 Mandatory Rules	7

4.2 Efficient Session Practices	7

4.3 Suggested CLAUDE.md Content (summary only)	7

4.4 Gate Kickoff Prompt Template	8

4.5 Gate Closure Report Template	8

4.6 Credit Checkpoints	8

5. Gate SC-1 — Foundation and Clinic Isolation (cap $7.00)	9

5.1 Objectives	9

5.2 Functional Requirements (40)	9

5.3 Backend Tasks	10

5.4 Frontend Tasks	11

5.5 Database Changes	11

5.6 Acceptance Tests (34)	12

5.7 Dependencies	12

5.8 Exit Criteria	13

5.9 Estimated Complexity	13

5.10 Credit-Spending Checkpoint	13

5.11 Explicitly Deferred Work	13

6. Gate SC-2 — Public QR Portal and Appointments (cap $9.00)	14

6.1 Objectives	14

6.2 Functional Requirements (28)	14

6.3 Backend Tasks	15

6.4 Frontend Tasks	15

6.5 Database Changes	15

6.6 Acceptance Tests (34)	16

6.7 Dependencies	16

6.8 Exit Criteria	17

6.9 Estimated Complexity	17

6.10 Credit-Spending Checkpoint	17

6.11 Explicitly Deferred Work	17

7. Gate SC-3 — Walk-In Tokens and Live Queue (cap $9.00)	18

7.1 Objectives	18

7.2 Functional Requirements (25)	18

7.3 Backend Tasks	19

7.4 Frontend Tasks	19

7.5 Database Changes	19

7.6 Acceptance Tests (37)	20

7.7 Dependencies	21

7.8 Exit Criteria	21

7.9 Estimated Complexity	21

7.10 Credit-Spending Checkpoint	21

7.11 Explicitly Deferred Work	21

8. Gate SC-4 — Dashboards, UX and E2E (cap $6.00)	22

8.1 Objectives	22

8.2 Functional Requirements (9)	22

8.3 Backend Tasks	22

8.4 Frontend Tasks	22

8.5 Database Changes	23

8.6 Acceptance Tests (11)	23

8.7 Dependencies	23

8.8 Exit Criteria	23

8.9 Estimated Complexity	23

8.10 Credit-Spending Checkpoint	23

8.11 Explicitly Deferred Work	24

9. Gate SC-5 — Release Readiness (cap $4.00)	25

9.1 Objectives	25

9.2 Functional Requirements (3)	25

9.3 Backend Tasks	25

9.4 Frontend Tasks	25

9.5 Database Changes	25

9.6 Acceptance Tests (2)	25

9.7 Dependencies	25

9.8 Exit Criteria	26

9.9 Estimated Complexity	26

9.10 Credit-Spending Checkpoint	26

9.11 Explicitly Deferred Work	26

10. Quality Assurance Strategy	27

10.1 Test Levels	27

10.2 Test Environments and Data	27

10.3 Required Quality Areas and Coverage	27

10.4 Key Test Designs	28

10.5 State-Transition Coverage	28

10.6 Supplementary and Revision B Tests	29

10.7 Regression and Defect Policy	30

11. Traceability Summary	31

11.1 Non-Functional Requirements by Gate	31

12. Consistency Review and Decision Status	33

13. Risks and Mitigations	34

14. Next Step	35

# 1. Document Control

| Field | Value |
| --- | --- |
| Document | Smart Clinic — Implementation and Quality Plan |
| Document ID | SC-PLAN-001 |
| Version | 1.1 (revision B, aligned with SRS v1.1 rev B and Technical Architecture v1.1 rev B) |
| Status | BASELINE CANDIDATE — revision B, ready for Product Owner freeze |
| Date | 26 October 2026 |
| Roles | Senior Technical Project Manager, QA Architect, Engineering Lead |
| Companion files | TRACEABILITY_MATRIX_v1.1.md, ACCEPTANCE_TEST_MATRIX_v1.1.csv, INCONSISTENCY_REGISTER_v1.1.md, README_DOCUMENTS.md |

## 1.1 Revision History

| Version | Date | Description |
| --- | --- | --- |
| 1.1 | 26 Oct 2026 | First implementation and QA baseline. |
| 1.1 rev B | 26 Oct 2026 | Baseline review: multi-clinic membership tasks and tests in SC-1; minimal CI from SC-1 (D-08); gate amounts restated as planning caps (D-06); FR-QUE-020 in SC-3; all register items decided; supplementary tests now part of SRS §16.8; counts updated (106 FRs, 118 tests, 98 endpoints, 47 capabilities). |

## 1.2 Approval

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Product Owner |  | Approve / Approve with changes / Reject |  |
| Engineering reviewer |  | Approve / Approve with changes / Reject |  |

# 2. Purpose, Inputs and Scope

This plan turns the approved SRS v1.1 and Technical Architecture v1.1 into five budget-capped implementation gates for Claude Code Cloud Sessions, together with the quality strategy that proves each gate. It changes no approved requirement and contains no application code.

| Input | Used for |
| --- | --- |
| SRS v1.1 rev B | 106 functional requirements (102 original + 4 added in rev B), 36 NFRs, 118 acceptance tests, business rules, state machines, permissions, decision record D-01…D-16, definition of done. |
| Technical Architecture v1.1 rev B | 20-table data model, 98 REST endpoints, algorithms, 38 ADRs, 47-capability permission matrix, diagrams. |
| Gate brief | Five gates SC-1…SC-5 with planning caps $7, $9, $9, $6, $4 (total allocation $35, D-06). |

Outputs of this plan: gate scopes and tasks (Sections 5–9), operating rules for Claude Code (Section 4), QA strategy (Section 10), traceability (Section 11 and TRACEABILITY_MATRIX_v1.1.md), acceptance test matrix (118 tests, all defined in SRS §16) and the inconsistency register (36 items, all decided).

# 3. Delivery Strategy

## 3.1 Gate Overview

| Gate | Name | Planning cap | FRs (MUST/SHOULD) | Tests | Complexity |
| --- | --- | --- | --- | --- | --- |
| SC-1 | Foundation and Clinic Isolation | $7.00 | 40 (37/3) | 34 | High |
| SC-2 | Public QR Portal and Appointments | $9.00 | 28 (26/2) | 34 | High |
| SC-3 | Walk-In Tokens and Live Queue | $9.00 | 25 (19/6) | 37 | Very high |
| SC-4 | Dashboards, UX and E2E | $6.00 | 9 (5/4) | 11 | Medium. |
| SC-5 | Release Readiness | $4.00 | 3 (2/1) | 2 | Low–Medium. |
| Total |  | $35.00 | 105 + 1 deferred | 118 |  |

Decision D-06: the USD 35 total allocation is retained; gate amounts are planning caps, not guarantees. A gate that reaches its cap stops and the Product Owner decides whether to continue within the remaining total or to defer scope.

## 3.2 Gate Sequence and Dependencies

| Gate | Depends on | Provides to later gates |
| --- | --- | --- |
| SC-1 | Approved documents; repository; Docker in session | Toolchain, contracts, auth and permission pipeline, ClinicContext, scheduling engine, audit writer, isolation and permission-matrix harnesses, UI shell and components. |
| SC-2 | SC-1 | Patients, appointments, exclusion constraint, tokens, idempotency, rate limiting, worker entry, public UI patterns. |
| SC-3 | SC-2 (patients, tokens, idempotency, appointments for check-in) | Queue data, outbox/SSE, day close, notification jobs. |
| SC-4 | SC-3 (queue data for metrics, live dashboard, E2E journeys) | Reports, completed security suite, accessible and responsive UI, E2E suite. |
| SC-5 | SC-4 | CI, release Docker configuration, demo seed, documentation, release sign-off. |

Gates are strictly sequential. Requirements that span gates (IR-12, IR-13) keep one owning gate and are re-verified when the dependent data arrives.

## 3.3 Gate Lifecycle

- Kickoff — user starts a new session with the kickoff prompt (4.4) and confirms the credit balance.

- Plan — the agent lists the tasks for the gate from Sections 5–9 in order and asks for approval of any migration it will need.

- Build — task by task; after each task, run only the targeted tests (rule R-07); commit with the task ID in the message.

- Checkpoints — status report at 50 % of the planning cap; apply the freeze list at 80 %; at 100 % stop and ask the Product Owner (D-06).

- Closure — full regression (all gates so far), concurrency tests ×10 where listed, db:verify, lint, type-check; CI green (from SC-1, D-08).

- Report — gate closure report (4.5); user updates the credit ledger; Product Owner approves the next gate.

# 4. Claude Code Cloud Operating Rules (Budget Discipline)

## 4.1 Mandatory Rules

| Rule | Instruction |
| --- | --- |
| R-01 | One agent only. Do not spawn subagents, parallel agents or background tasks. |
| R-02 | Read each planning document once per session at most. Use CLAUDE.md (gate summary) and the traceability matrix rows for the current gate; open the SRS/architecture only for the specific section a task needs. |
| R-03 | Work only inside the current gate. Do not start tasks from a later gate, even if convenient. |
| R-04 | Database migrations: show the generated SQL (including hand-written constraints) and wait for explicit approval before applying. Never edit an applied migration. |
| R-05 | No seeds, data resets, `prisma migrate reset`, `DROP`, `TRUNCATE`, force pushes or file deletions outside your own new files without explicit approval. Test-database fixtures created and destroyed by the test runner are allowed. |
| R-06 | No paid infrastructure, external services, SaaS accounts or new hosted resources without approval. No SMS/email providers at all (SRS 4.2). |
| R-07 | During development run only the targeted tests for the touched module (e.g. `pnpm vitest run modules/queue`). Run the full regression only at gate closure. |
| R-08 | Reuse existing components, helpers, factories and contracts before writing new ones. Do not add dependencies without stating why. |
| R-09 | Keep diffs small; avoid reformatting untouched files; do not regenerate whole files to change a few lines. |
| R-10 | Do not paste large files or logs into the conversation; summarise failures with the first relevant lines. |
| R-11 | Gate amounts are planning caps, not guarantees (D-06). At 50 % send a status report; at 80 % apply the gate’s freeze list; at 100 % stop and ask the Product Owner whether to continue (within the USD 35 total) or defer. |
| R-12 | Stop at the gate boundary: deliver the gate report and wait for written confirmation before starting the next gate. |
| R-13 | After each gate, the user records the Claude Cloud credit balance in the credit ledger; the next gate starts only with the ledger updated. |
| R-14 | Never invent requirements. If the SRS, architecture and this plan disagree, stop and add an entry to INCONSISTENCY_REGISTER rather than choosing silently. |
| R-15 | Use only fictional data. Never paste or generate real patient information. |

## 4.2 Efficient Session Practices

- Keep a short `CLAUDE.md` at the repository root (4.3) so the agent does not need to re-read long documents.

- Give the agent the exact gate rows from TRACEABILITY_MATRIX_v1.1.md instead of whole documents.

- Prefer editing existing files over creating new ones; prefer generated contracts and factories over hand-written duplicates.

- Batch related small changes into one task; avoid back-and-forth on formatting.

- When a test fails, fix the first failure and re-run only that file.

- Use the Docker database already running; do not rebuild images unless dependencies changed.

- Do not run Playwright during SC-1…SC-3 except for the specific journey being built (E2E is consolidated in SC-4).

## 4.3 Suggested CLAUDE.md Content (summary only)

Project: Smart Clinic (portfolio). Fictional data only.

Authoritative docs (Baseline v1.1 rev B): SRS > Architecture > ADR log > Plan.

Current gate: SC-n — <name>. Planning cap $X (not a guarantee). Report at 50 %, freeze at 80 %, stop and ask at 100 %.

Rules: one agent; no subagents; no unapproved migrations, seeds, resets or deletes;

no paid services; targeted tests during work; full regression at gate closure;

stop at gate boundary and write the gate report.

Stack: pnpm monorepo; React+TS+Vite+Tailwind; Express; Prisma; PostgreSQL 16; Zod; SSE; Vitest; Playwright.

Invariants: clinic_id from the session’s selected membership (re-validated, X-Clinic-Id must match) or token only;

one account → many clinic memberships (UNIQUE clinic_id,user_id); composite FKs; exclusion constraint on appointments;

queue_counter row lock for tokens; REGISTERED is not WAITING; tokens stored as hashes.

Commands: pnpm test:unit <path> | pnpm test:int <path> | pnpm db:verify | pnpm lint | pnpm typecheck

## 4.4 Gate Kickoff Prompt Template

You are the single engineering agent for Smart Clinic. Gate: SC-n (<name>). Cap $X.

Scope: tasks SCn-BE-* and SCn-FE-* in Plan v1.1 §<n>; FRs listed in TRACEABILITY_MATRIX rows for SC-n.

Do not start other gates. Do not use subagents.

First reply with: (1) ordered task list, (2) migrations you will need (SQL shown for approval

before applying), (3) questions on any IR items marked “Needed before SC-n”.

Then wait for my approval.

## 4.5 Gate Closure Report Template

| Section | Content |
| --- | --- |
| Scope delivered | Task IDs and FR IDs completed. |
| Scope deferred | FR/task IDs moved by freeze list, with reason. |
| Tests | Counts pass/fail/blocked from the acceptance matrix for this gate; full regression result; concurrency ×10 results. |
| Database | Migrations applied (names) and db:verify result. |
| Defects | Open defects by severity. |
| Decisions needed | IR items and new questions. |
| Credit | Estimate of spend; user confirms actual balance in the ledger. |

## 4.6 Credit Checkpoints

| Gate | Planning cap | 50 % report | 80 % freeze | 100 %: stop and ask PO |
| --- | --- | --- | --- | --- |
| SC-1 | $7.00 | $3.50 | $5.60 | $7.00 |
| SC-2 | $9.00 | $4.50 | $7.20 | $9.00 |
| SC-3 | $9.00 | $4.50 | $7.20 | $9.00 |
| SC-4 | $6.00 | $3.00 | $4.80 | $6.00 |
| SC-5 | $4.00 | $2.00 | $3.20 | $4.00 |

Gate amounts are planning caps, not guarantees (D-06). Unspent credit is not automatically available to the next gate; any reallocation within the USD 35 total requires Product Owner approval and is recorded in the ledger (README_DOCUMENTS.md §5). No Claude Code Cloud credits are used until the Product Owner approves SC-1 kickoff.

# 5. Gate SC-1 — Foundation and Clinic Isolation (cap $7.00)

## 5.1 Objectives

- Create the monorepo, toolchain and Docker Compose development stack that every later gate reuses.

- Deliver staff authentication, sessions, CSRF, lockout and the permission pipeline compiled from PERMISSION_MATRIX_v1.1.csv.

- Deliver the multi-clinic staff model: global accounts, one membership per clinic with its own roles and activation, clinic selection and switching, per-request membership re-validation and the X-Clinic-Id consistency check (D-01). This is core scope and is protected by the freeze list (D-07).

- Deliver a minimal GitHub Actions CI workflow (D-08).

- Deliver platform clinic lifecycle and clinic configuration: profile, settings, opening hours, breaks, closures, services, doctors, weekly schedules and exceptions.

- Establish tenant isolation in the schema (composite FKs) and in code (ClinicContext), with an isolation test harness that later gates extend.

- Deliver the pure availability-interval engine with time-zone and DST handling (used by SC-2 and SC-3).

- Deliver a basic, accessible staff UI shell and admin configuration screens.

## 5.2 Functional Requirements (40)

| FR | Priority | Requirement (abridged — SRS §7 is authoritative) |
| --- | --- | --- |
| FR-PLT-001 | MUST | The Platform Administrator shall create a clinic tenant with name, slug, IANA time zone and the first Clinic Admin’s… |
| FR-PLT-002 | MUST | The Platform Administrator shall activate a clinic only when the setup checklist passes: weekly operating hours… |
| FR-PLT-003 | MUST | The Platform Administrator shall suspend and reactivate a clinic, with a mandatory reason. While SUSPENDED: the public… |
| FR-PLT-004 | MUST | The Platform Administrator shall see a clinic list with metadata (name, slug, status, created date, active membership… |
| FR-PLT-005 | SHOULD | The Platform Administrator shall be able to reset any staff account’s password to a one-time temporary password. This… |
| FR-PLT-006 | SHOULD | The Platform Administrator shall deactivate and reactivate a global staff account with a mandatory reason. Deactivation… |
| FR-CLN-001 | MUST | Clinic Admin shall maintain the clinic profile: display name, address, contact phone, IANA time zone, default phone… |
| FR-CLN-002 | MUST | Each clinic shall have a globally unique slug (BR-010). The slug is editable only while PENDING_SETUP and becomes… |
| FR-CLN-003 | MUST | Clinic Admin shall define weekly operating hours: for each weekday either CLOSED or one opening time and one closing… |
| FR-CLN-004 | MUST | Clinic Admin shall create, edit and delete closures: full-day (one or more dates, e.g. public holidays) or partial (a… |
| FR-CLN-005 | MUST | Clinic Admin shall configure booking settings: slot granularity (5, 10, 15, 20, 30 or 60 min; default 15), reservation… |
| FR-CLN-006 | MUST | Clinic Admin shall configure walk-in settings: QR walk-in enabled (yes/no), daily walk-in capacity (1–500),… |
| FR-STF-001 | MUST | Clinic Admin shall add staff to the clinic by email with one or more clinic roles: CLINIC_ADMIN, RECEPTIONIST, DOCTOR.… |
| FR-STF-002 | MUST | A newly created global account shall receive a one-time temporary password, displayed once to the creator, and must… |
| FR-STF-003 | MUST | Clinic Admin shall deactivate and reactivate staff memberships in their clinic. Deactivation shall revoke the user’s… |
| FR-STF-004 | MUST | Each clinic shall always have at least one active membership with the CLINIC_ADMIN role; the system shall prevent… |
| FR-STF-005 | SHOULD | Clinic Admin shall reset a staff user’s password to a temporary password only when that user has no membership in any… |
| FR-STF-006 | MUST | Any staff user shall change their own password. |
| FR-STF-007 | MUST | A staff user with more than one active membership shall select the active clinic after login and may switch between… |
| FR-SVC-001 | MUST | Clinic Admin shall create and edit services with: name (2–80 chars), short operational description (≤ 300 chars, no… |
| FR-SVC-002 | MUST | Clinic Admin shall assign one or more eligible doctors to each service. |
| FR-SVC-003 | MUST | A service shall not be deleted once it has any appointment or queue entry; it may be deactivated. Inactive services are… |
| FR-DOC-001 | MUST | Clinic Admin shall create doctor profiles with display name, public title/specialty label (non-clinical, e.g. “General… |
| FR-DOC-002 | MUST | Clinic Admin shall define each doctor’s weekly schedule: per weekday, not working or one start and end time with zero… |
| FR-DOC-003 | MUST | Clinic Admin shall add schedule exceptions for a doctor: unavailable (full day or time range, e.g. leave) or modified… |
| FR-DOC-004 | MUST | A doctor’s bookable time shall be the intersection of clinic availability and doctor availability (Section 12). Doctor… |
| FR-DOC-005 | MUST | A Doctor user shall view their own schedule, exceptions and appointments for any date, but not those of other doctors. |
| FR-SEC-001 | MUST | Staff shall authenticate with email and password. Passwords shall be hashed with Argon2id (or bcrypt cost ≥ 12 if… |
| FR-SEC-002 | MUST | Sessions shall use server-side session records referenced by an HttpOnly, Secure, SameSite=Lax cookie; idle timeout 60… |
| FR-SEC-003 | MUST | After 5 failed logins for one account within 15 min, further attempts shall be delayed/blocked for 15 min; responses… |
| FR-SEC-004 | MUST | Every staff API request shall be authorised server-side against the permissions matrix (Section 10). UI hiding is not a… |
| FR-SEC-005 | MUST | The clinic context shall be derived only from the session’s selected active membership (staff) or the clinic… |
| FR-SEC-008 | MUST | All API inputs shall be validated with shared Zod schemas; unknown fields shall be rejected. |
| FR-SEC-009 | MUST | State-changing staff requests shall be protected against CSRF (SameSite cookie plus synchroniser or double-submit… |
| FR-SEC-010 | MUST | Logs shall not contain access tokens, reservation secrets, passwords or full phone numbers; URLs containing tokens… |
| FR-SEC-011 | MUST | Platform Administrator accounts shall have no permission on clinic-tenant patient, appointment or queue resources, and… |
| FR-SEC-012 | MUST | Every staff request shall carry the client’s expected active clinic (X-Clinic-Id header). The server shall reject the… |
| FR-AUD-001 | MUST | The system shall record an audit event for: logins (success/failure), logout, clinic selection and switching, password… |
| FR-AUD-002 | MUST | Each event shall store: event ID, UTC timestamp, clinic ID (nullable for platform events), actor type (STAFF,… |
| FR-AUD-003 | MUST | Audit records shall be append-only: the application database role shall have no UPDATE or DELETE privilege on the audit… |

Non-functional requirements addressed: NFR-MNT-001, NFR-MNT-002, NFR-TST-001 (scheduling), NFR-TST-003, NFR-OPS-001, NFR-DAT-001, NFR-I18N-001, NFR-SEC-002 (headers), NFR-SEC-004 (harness).

## 5.3 Backend Tasks

| Task | Description |
| --- | --- |
| SC1-BE-01 | pnpm workspace: apps/web, apps/api, packages/contracts, packages/config; TypeScript strict; ESLint module-boundary rule; Vitest config (unit + integration projects). |
| SC1-BE-02 | Docker Compose dev stack: db (PostgreSQL 16), api, web; .env.example. Worker service added in SC-2. Minimal GitHub Actions workflow: install, lint, type-check, unit + integration tests with a PostgreSQL service (D-08). |
| SC1-BE-03 | HTTP infrastructure: request ID, helmet headers, pino logger with redaction list, error envelope + code mapping, Zod validation middleware (.strict), injectable Clock, Luxon time utilities. |
| SC1-BE-04 | identity module: login, logout, me (memberships), change-password, select-clinic; Argon2id; server-side sessions (hashed IDs, idle 60 min / absolute 12 h, selected membership with composite FK); lockout; CSRF token + Origin check (rotated on switch); forced password change. |
| SC1-BE-05 | Authorisation pipeline: resolveClinicContext from the selected membership (re-validated per request: membership active, same user, clinic accessible, account active), X-Clinic-Id check (409 on mismatch), clinicStatusGate (SUSPENDED read-only), requirePermission from compiled matrix, scopeGuard (doctor own). |
| SC1-BE-06 | platform module: create clinic + first Clinic Admin membership (new or existing account), setup checklist, activate / suspend / reactivate (reason), account lookup, account password reset (FR-PLT-005, SHOULD), global account deactivate/reactivate (FR-PLT-006, SHOULD), clinic list with aggregates available so far. |
| SC1-BE-07 | clinic module: profile, settings (booking and walk-in settings stored and validated; walk-in enforcement in SC-3), business hours (replace whole week), closures CRUD; slug/timezone lock after activation. |
| SC1-BE-08 | Staff membership management: add by email (new account with temporary password, or membership for an existing account without password change), edit roles, deactivate/reactivate membership (clinic access only), reset password only for single-clinic accounts (BR-084), last-admin protection. |
| SC1-BE-09 | Services and doctor eligibility CRUD; delete only when unreferenced, otherwise deactivate. |
| SC1-BE-10 | scheduling module: doctor profiles (optional member link), weekly availability, exceptions, schedule view; pure availability-interval engine (clinic ∩ doctor − breaks − closures − exceptions) with DST rules. |
| SC1-BE-11 | audit module: append-only writer used inside transactions; events for all SC-1 actions. |
| SC1-BE-12 | Test harness: factories, two test clinics (Asia/Bangkok, Europe/London) in the test database only, a fixture user with memberships in both clinics, route-iterating isolation test (also run as the dual-membership user), permission-matrix test generator. |

## 5.4 Frontend Tasks

| Task | Description |
| --- | --- |
| SC1-FE-01 | Vite + React + TypeScript + Tailwind scaffold; router with realms (public, app, platform, display); auth guard; API client typed by contracts; design tokens. |
| SC1-FE-02 | Reusable components: form field, select, time-interval editor (open/close + breaks), data table, dialog, toast, empty/loading/error states. |
| SC1-FE-03 | S-01 Login, S-02 Change password, S-03 Select clinic; header clinic switcher; API client sends X-Clinic-Id and reloads on 409/403 selection errors. |
| SC1-FE-04 | PA-01 Clinics and accounts (create, activate, suspend, reactivate; account lookup, password reset, deactivate/reactivate). |
| SC1-FE-05 | A-01 Settings, A-02 Hours & closures, A-03 Services, A-04 Doctors & schedules, A-05 Staff. |
| SC1-FE-06 | D-02 My schedule (hours and exceptions; appointments added in SC-2). |

## 5.5 Database Changes

- Migration 0001: extensions (btree_gist, citext, pg_trgm, pgcrypto), all enums, roles sc_owner/sc_app.

- Migration 0002: app_user, session (selected membership columns + composite FK to clinic_member (clinic_id, id, user_id)), clinic, clinic_member (UNIQUE (clinic_id, user_id), UNIQUE (clinic_id, id, user_id)), doctor, clinic_business_hour, clinic_closure, clinic_service, doctor_service, doctor_availability, schedule_exception, audit_log; UNIQUE (clinic_id, id) and composite FKs; CHECKs; exclusion constraints on hour intervals; trigger clinic_lock_after_activation; REVOKE UPDATE/DELETE/TRUNCATE on audit_log from sc_app.

- db:verify manifest for every hand-written object.

Every migration is shown as SQL and approved before it is applied (rule R-04).

## 5.6 Acceptance Tests (34)

| Test | Quality area | Level | Origin |
| --- | --- | --- | --- |
| TC-CLN-001 | Clinic opening/closing hours | U/I | SRS |
| TC-CLN-003 | Clinic configuration | E | SRS |
| TC-DOC-001 | Doctor schedules and breaks | U/I | SRS |
| TC-DOC-002 | Doctor schedules and breaks | U | SRS |
| TC-DOC-003 | Doctor schedules and breaks | I | SRS |
| TC-NFR-007 | Database integrity | I | SRS |
| TC-PLT-001 | Platform administration | I/E | SRS |
| TC-PLT-003 | Platform administration | I | SRS |
| TC-PLT-004 | Multi-clinic membership | I | SRS |
| TC-SCH-001 | Timezone and DST | U | SRS |
| TC-SCH-002 | Timezone and DST | U | SRS |
| TC-SCH-003 | Timezone and DST | U | SRS |
| TC-SCH-004 | Doctor schedules and breaks | U/I | SRS |
| TC-SCH-005 | Clinic opening/closing hours | U | SRS |
| TC-SCH-006 | Clinic opening/closing hours | U | SRS |
| TC-SEC-001 | Strict tenant isolation | I | SRS |
| TC-SEC-002 | Strict tenant isolation | I | SRS |
| TC-SEC-003 | Staff role authorization | I | SRS |
| TC-SEC-004 | Staff role authorization | I | SRS |
| TC-SEC-008 | Audit | I | SRS |
| TC-SEC-009 | Staff authentication | I | SRS |
| TC-SEC-010 | Staff authentication | I | SRS |
| TC-SEC-012 | Strict tenant isolation | I | SRS |
| TC-SEC-013 | Staff role authorization | I | SRS |
| TC-SEC-016 | Staff role authorization | I | SRS |
| TC-SEC-017 | Strict tenant isolation | I | SRS |
| TC-STF-001 | Staff authentication | E | SRS |
| TC-STF-002 | Staff authentication | I | SRS |
| TC-STF-003 | Staff authentication | I | SRS |
| TC-STF-004 | Multi-clinic membership | I | SRS |
| TC-STF-005 | Multi-clinic membership | I | SRS |
| TC-STF-006 | Staff role authorization | I | SRS |
| TC-SVC-001 | Clinic configuration | I | SRS |
| TC-VAL-003 | Phone and name validation | I | SRS |

Full scenarios and expected results: ACCEPTANCE_TEST_MATRIX_v1.1.csv (filter gate = SC-1). At gate closure every earlier gate’s tests are re-run as part of the full regression.

## 5.7 Dependencies

Baseline v1.1 (rev B) frozen by the Product Owner; GitHub repository created by the user; Docker available in the Claude Code Cloud session; explicit SC-1 kickoff approval. Decisions D-01, D-07, D-08 and D-11 apply.

## 5.8 Exit Criteria

- All SC-1 MUST FRs implemented; their mapped tests pass (targeted + full SC-1 regression).

- Multi-clinic membership tests TC-STF-004, -005, -006, TC-PLT-004 and TC-SEC-017 pass.

- CI workflow green on the gate commit.

- db:verify green on a clean database; migrations reviewed and approved before execution.

- Isolation harness passes for every SC-1 tenant route; permission-matrix test passes for SC-1 capabilities.

- Lint, type-check and unit/integration suites green; no Critical/High defects open.

- Gate report delivered (scope done, deferred, credit spent, decisions needed); session stops for approval.

## 5.9 Estimated Complexity

High (broadest gate: 12 backend and 6 frontend task groups, 12 tables, multi-clinic identity). Highest budget risk relative to its planning cap.

## 5.10 Credit-Spending Checkpoint

Budget control for SC-1 Report at $3.50 spent. At $5.60 (80 %) freeze (D-07): finish MUST items only — the tenant and membership model is never deferred; defer in order FR-PLT-006, FR-PLT-005, FR-STF-005 (SHOULD), PA-01 account screens, D-02 polish. At $7.00 (planning cap) stop and ask the Product Owner (D-06). The amount is a planning cap, not a guarantee (D-06). The user records the credit balance in the ledger after closure (rule R-13).

## 5.11 Explicitly Deferred Work

- Clinic logo upload (FR-CLN-001 COULD) and per-doctor walk-in cap (FR-CLN-006 COULD) — D-05.

- Walk-in settings enforcement (SC-3); conflicts view (SC-2); appointment aggregates in PA-01 and appointments in D-02 (SC-2).

- Worker process (SC-2); CI extension with Playwright and concurrency runs (SC-5); demo seed (SC-5).

# 6. Gate SC-2 — Public QR Portal and Appointments (cap $9.00)

## 6.1 Objectives

- Deliver the permanent clinic QR code and public portal.

- Deliver Journey A end to end: service → doctor → date/time → reservation hold → confirmation → booking reference and private link.

- Guarantee no double booking under concurrency (exclusion constraint) and safe rescheduling.

- Deliver secure access tokens, idempotency, rate limiting and the patient record rules.

- Deliver staff appointment management and the conflicts view.

## 6.2 Functional Requirements (28)

| FR | Priority | Requirement (abridged — SRS §7 is authoritative) |
| --- | --- | --- |
| FR-CLN-008 | MUST | Changes to hours, closures, schedules or services shall not alter or cancel existing CONFIRMED appointments. The system… |
| FR-CLN-009 | MUST | The public clinic portal shall be available only when the clinic status is ACTIVE. |
| FR-SVC-004 | MUST | A service with zero active eligible doctors shall not be offered publicly. |
| FR-PAT-001 | MUST | The system shall store a clinic-scoped patient record containing only: full name as entered, normalised phone (E.164),… |
| FR-PAT-002 | MUST | On public or staff registration, the system shall reuse an existing patient in the same clinic where normalised phone… |
| FR-PAT-006 | MUST | Patient records shall never be linked, matched or searchable across clinics, including where the same phone number… |
| FR-QR-001 | MUST | Each clinic shall have exactly one permanent QR code that encodes only the canonical public URL https://<host>/c/<slug>… |
| FR-QR-002 | MUST (poster SHOULD) | Clinic Admin shall download the QR code as PNG (≥ 1024 px) and SVG, and a printable A4 poster with clinic name, short… |
| FR-QR-003 | MUST | The QR code and public URL shall remain valid for the life of the clinic regardless of settings changes. |
| FR-QR-004 | MUST | The public portal shall show clinic name, address, contact phone, today’s opening hours or closure label, walk-in… |
| FR-QR-005 | MUST | Each portal action shall be disabled with a plain-language reason when unavailable (e.g. no bookable services; walk-ins… |
| FR-APT-001 | MUST | The public booking flow shall list active services with online booking enabled and ≥ 1 active eligible doctor, showing… |
| FR-APT-002 | MUST | If exactly one eligible doctor exists for the chosen service, that doctor shall be preselected and shown; if several… |
| FR-APT-003 | MUST | The system shall return available start times for a given service, doctor and date, and the list of dates with… |
| FR-APT-004 | MUST | Availability shall be computed according to Section 12, honouring clinic hours, clinic breaks, closures, doctor hours,… |
| FR-APT-005 | MUST | Selecting a time shall create a reservation: a PENDING appointment holding that doctor-time range for the hold period,… |
| FR-APT-006 | MUST | Confirmation shall require reservation ID, reservation secret, name, phone, privacy-notice acknowledgement and… |
| FR-APT-007 | MUST | On confirmation, the system shall generate a unique booking reference (BR-020) and a private access token (BR-022), and… |
| FR-APT-008 | MUST | The private booking page shall show clinic, service, doctor, date/time, status, booking reference, the patient’s first… |
| FR-APT-009 | SHOULD | The patient shall cancel a CONFIRMED appointment from the private page until the cancellation cutoff; after the cutoff,… |
| FR-APT-010 | MUST | Clinic Admin and Receptionist shall create appointments on a patient’s behalf. Staff-created appointments are created… |
| FR-APT-011 | MUST (reschedule SHOULD) | Clinic Admin and Receptionist shall cancel (with reason) and reschedule CONFIRMED appointments. Rescheduling keeps the… |
| FR-APT-014 | MUST | PENDING appointments past expiry shall be treated as non-blocking immediately (query-time check) and set to EXPIRED by… |
| FR-APT-015 | MUST | Staff shall view appointments as a day list per doctor and a filterable list (date range, doctor, service, status). |
| FR-APT-016 | MUST | The system shall show a “Conflicts” view of future CONFIRMED appointments that no longer fit current hours, closures,… |
| FR-APT-017 | SHOULD | The system shall reject public confirmation when the phone already has the configured maximum number of active future… |
| FR-SEC-006 | MUST | Private access tokens shall be generated with a CSPRNG (≥ 256 bits, base64url), stored only as SHA-256 hashes, compared… |
| FR-SEC-007 | MUST | Public endpoints shall be rate-limited per IP and per clinic (Section 14.5) and return 429 with Retry-After when… |

Non-functional requirements addressed: NFR-PERF-002 (measured informally), NFR-REL-003, NFR-PRIV-001..003, NFR-RESP-001 (public screens built mobile-first).

## 6.3 Backend Tasks

| Task | Description |
| --- | --- |
| SC2-BE-01 | patients module: normalisation (name, phone via libphonenumber-js), matching rule, upsert. |
| SC2-BE-02 | Public portal endpoints: clinic portal status, services (booking mode, eligible doctors), date and slot availability using the SC-1 engine. |
| SC2-BE-03 | Hold (AT-01) with stale-hold expiry, hold cookie, per-IP hold limit; release (AT-04). |
| SC2-BE-04 | Confirm (AT-02): secret check, expiry, re-validation, per-phone limit, booking reference generator, BOOKING token. |
| SC2-BE-05 | Idempotency middleware with AES-256-GCM encrypted response bodies; rate limiter for public and login routes. |
| SC2-BE-06 | Token-scoped endpoints: GET booking, cancel (cutoff), calendar.ics (SHOULD). |
| SC2-BE-07 | Staff appointments: availability (staff mode), create, list/day view, get, reschedule (single conditional UPDATE), cancel; conflicts computed on read. |
| SC2-BE-08 | QR PNG/SVG endpoints for the canonical URL. |
| SC2-BE-09 | Worker entry (same image) with hold-expiry sweep; Compose service added. |
| SC2-BE-10 | Extend audit events, isolation harness and permission-matrix test to SC-2 routes; add appointment aggregates to PA-01 and appointments to D-02 data. |

## 6.4 Frontend Tasks

| Task | Description |
| --- | --- |
| SC2-FE-01 | P-01 portal, P-02 service, P-03 doctor (auto-skip), P-04 date/time, P-05 details + hold countdown, P-06 confirmed, P-07 my booking, P-11 system pages. |
| SC2-FE-02 | R-03 appointments (day list per doctor + filter list), R-04 new/edit, R-07 conflicts. |
| SC2-FE-03 | A-06 QR page and printable poster route (poster SHOULD). |

## 6.5 Database Changes

- Migration 0003: patient (generated phone_last4, trigram index, partial unique), appointment (exclusion constraint, partial unique hold cookie, CHECKs, status guard trigger), public_access_token (purpose CHECKs, partial uniques), idempotency_record.

- db:verify manifest extended.

Every migration is shown as SQL and approved before it is applied (rule R-04).

## 6.6 Acceptance Tests (34)

| Test | Quality area | Level | Origin |
| --- | --- | --- | --- |
| TC-APT-001 | Appointment journey | E | SRS |
| TC-APT-002 | Appointment journey | E | SRS |
| TC-APT-003 | Clinic opening/closing hours | U | SRS |
| TC-APT-004 | Doctor schedules and breaks | U | SRS |
| TC-APT-005 | Appointment journey | I | SRS |
| TC-APT-006 | Concurrent appointment booking | I | SRS |
| TC-APT-007 | Appointment journey | I | SRS |
| TC-APT-008 | Phone and name validation | U/I | SRS |
| TC-APT-009 | Public access privacy | E | SRS |
| TC-APT-010 | Appointment journey | I | SRS |
| TC-APT-011 | Appointment journey | I/E | SRS |
| TC-APT-014 | Appointment journey | I | SRS |
| TC-APT-015 | Booking rules | U/I | SRS |
| TC-APT-016 | Appointment journey | E | SRS |
| TC-APT-017 | Concurrent rescheduling | I | SRS |
| TC-APT-018 | Appointment journey | I | SRS |
| TC-APT-019 | Concurrent rescheduling | I | SRS |
| TC-APT-020 | Concurrent rescheduling | I | SRS |
| TC-APT-021 | Concurrent appointment booking | I | SRS |
| TC-APT-022 | Public access privacy | I | SRS |
| TC-APT-023 | Public access privacy | I | SRS |
| TC-PAT-001 | Phone and name validation | U/I | SRS |
| TC-PLT-002 | Platform administration | E | SRS |
| TC-QR-001 | QR portal | E | SRS |
| TC-QR-002 | QR portal | E | SRS |
| TC-QR-003 | QR portal | I | SRS |
| TC-QR-004 | QR portal | M | SRS |
| TC-SEC-005 | Public access privacy | I | SRS |
| TC-SEC-006 | Public access privacy | I | SRS |
| TC-SEC-011 | Public access privacy | M/I | SRS |
| TC-SEC-014 | Staff role authorization | I | SRS |
| TC-SEC-015 | Public access privacy | I | SRS |
| TC-VAL-001 | Phone and name validation | U | SRS |
| TC-VAL-002 | Phone and name validation | U | SRS |

Full scenarios and expected results: ACCEPTANCE_TEST_MATRIX_v1.1.csv (filter gate = SC-2). At gate closure every earlier gate’s tests are re-run as part of the full regression.

## 6.7 Dependencies

SC-1 closed (auth, permissions, scheduling engine, services, doctors). Decisions D-04 (encrypted idempotency) and D-16 (hold cookie in privacy notice) apply.

## 6.8 Exit Criteria

- Journey A demonstrable on a mobile viewport with fictional test data.

- TC-APT-006, TC-APT-019, TC-APT-020, TC-APT-021 pass 10 consecutive runs.

- No raw tokens or secrets in database or logs (TC-SEC-011, TC-SEC-015).

- All SC-2 MUST FR tests and full regression (SC-1 + SC-2) green; gate report; stop for approval.

## 6.9 Estimated Complexity

High (concurrency, tokens, idempotency, 11 public/staff screens).

## 6.10 Credit-Spending Checkpoint

Budget control for SC-2 Report at $4.50. At $7.20 freeze: defer .ics (FR-APT-007 SHOULD), QR poster (FR-QR-002 SHOULD), patient self-cancel UI polish (FR-APT-009 SHOULD), FR-APT-017 (SHOULD) in that order. At $9.00 (planning cap) stop and ask the Product Owner (D-06). The amount is a planning cap, not a guarantee (D-06). The user records the credit balance in the ledger after closure (rule R-13).

## 6.11 Explicitly Deferred Work

- Check-in and no-show (SC-3); patient search (SC-3); conflict alert notifications (SC-3).

- FR-QR-006 portal visit counts (COULD) — deferred beyond MVP.

# 7. Gate SC-3 — Walk-In Tokens and Live Queue (cap $9.00)

## 7.1 Objectives

- Deliver Journey B: same-day QR walk-in with eligibility, capacity, cutoff and duplicate rules; REGISTERED status distinct from WAITING.

- Deliver gapless daily tokens shared by walk-ins and check-ins.

- Deliver reception check-in and arrival confirmation, the doctor workspace and every queue transition with concurrency protection.

- Deliver the outbox, SSE hub and live updates for staff, doctors, patients and the waiting-room display.

- Deliver day close, no-show automation and in-app staff alerts.

## 7.2 Functional Requirements (25)

| FR | Priority | Requirement (abridged — SRS §7 is authoritative) |
| --- | --- | --- |
| FR-CLN-007 | SHOULD | Clinic Admin or Receptionist shall pause and resume QR walk-in registration for today. Pause takes effect for all new… |
| FR-DOC-006 | SHOULD | A Doctor or Receptionist shall mark a doctor “unavailable for the rest of today”, which creates a same-day exception,… |
| FR-PAT-003 | MUST | Staff shall search patients, appointments and queue entries in their clinic by phone (full or last 4 digits), name… |
| FR-APT-012 | MUST | Receptionist or Clinic Admin shall check in a CONFIRMED appointment within the check-in window (override with reason… |
| FR-APT-013 | MUST | Staff shall mark a CONFIRMED appointment NO_SHOW after the no-show grace period. At clinic day close, remaining… |
| FR-QUE-001 | MUST | “Join Today’s Queue” shall check eligibility (Section 12.6) before showing the form and again inside the registration… |
| FR-QUE-002 | MUST | The walk-in flow shall list only active services with walk-in enabled and, per service, only doctors with remaining… |
| FR-QUE-003 | MUST | Walk-in registration shall require name, phone, privacy-notice acknowledgement and idempotency key (same validation as… |
| FR-QUE-004 | MUST | Each queue entry shall receive a token number unique per clinic per clinic-local date, allocated sequentially from 1… |
| FR-QUE-005 | MUST | A QR walk-in entry shall be created with status REGISTERED. The patient shall immediately see the token, status and… |
| FR-QUE-006 | MUST | Receptionist or Clinic Admin shall register a staff walk-in for a patient who is present, with name and phone (no-phone… |
| FR-QUE-007 | MUST | Receptionist or Clinic Admin shall confirm arrival of a REGISTERED entry, moving it to WAITING and recording arrived_at. |
| FR-QUE-008 | MUST | Each doctor shall have an ordered waiting line of WAITING entries ordered by queue sort time ascending, then token… |
| FR-QUE-009 | MUST | The doctor (or Clinic Admin on the doctor’s behalf) shall “Call next”, which moves the head of that doctor’s waiting… |
| FR-QUE-010 | MUST | The doctor (or Clinic Admin) shall Start (CALLED → IN_CONSULTATION) and Complete (IN_CONSULTATION → COMPLETED).… |
| FR-QUE-011 | MUST | Authorised staff shall: return a CALLED entry to WAITING (patient absent; keeps original sort time and increments… |
| FR-QUE-012 | MUST | A doctor shall have at most one entry in CALLED or IN_CONSULTATION at any time (enforced by database constraint). |
| FR-QUE-013 | MUST | Queue changes shall be pushed via SSE to authorised subscribers: clinic staff stream, doctor stream, waiting-room… |
| FR-QUE-014 | MUST | The patient status page shall show: token, status in plain language, doctor display name, “now serving” token for that… |
| FR-QUE-015 | SHOULD | The patient shall leave the queue from the status page while REGISTERED or WAITING (→ CANCELLED by PATIENT), after a… |
| FR-QUE-016 | MUST | At clinic day close (performed within 5 minutes after local midnight) the system shall finalise non-terminal entries:… |
| FR-QUE-017 | SHOULD | A waiting-room display screen (staff-launched, kiosk mode) shall show, per doctor, the token now being called and the… |
| FR-QUE-018 | MUST | Public walk-in registration shall be rejected when the same normalised phone already has a non-terminal queue entry at… |
| FR-QUE-019 | SHOULD | Receptionist or Clinic Admin shall reassign a WAITING entry to another doctor who offers the same service and is… |
| FR-QUE-020 | SHOULD | Receptionist-assisted no-phone exception (separate staff workflow): for a patient who is physically present and has no… |

Non-functional requirements addressed: NFR-PERF-004, NFR-REL-001, NFR-REL-002, NFR-PERF-006 (smoke), NFR-ACC-002 (live regions built in).

## 7.3 Backend Tasks

| Task | Description |
| --- | --- |
| SC3-BE-01 | queue module: counter-row allocation algorithm, eligibility service, QR walk-in (name + phone mandatory, no bypass), staff walk-in (override reason), no-phone staff exception (FR-QUE-020, SHOULD), duplicate-phone rule (QR only, D-03). |
| SC3-BE-02 | Check-in (AT-08 + QT-02) with window/override; appointment no-show (manual). |
| SC3-BE-03 | Transitions: confirm-arrival, call-next (head, SKIP LOCKED), call specific, start, complete, return-to-waiting (recall limit), no-show, cancel, reassign; AT-10/AT-11 cascade. |
| SC3-BE-04 | Ordering and positions (BR-060/061); public queue status; leave queue with capacity release. |
| SC3-BE-05 | Walk-in pause/resume; doctor unavailable-for-today; unified staff search. |
| SC3-BE-06 | realtime: clinic_event outbox writer, pg LISTEN client, SSE hub with audience routing, three streams, heartbeat, credential re-validation, per-IP stream caps. |
| SC3-BE-07 | Display keys (DISPLAY tokens) and board endpoints (SHOULD). |
| SC3-BE-08 | Worker: day close per clinic time zone, notification jobs (SCHEDULE_CONFLICTS_DETECTED, DOCTOR_UNAVAILABLE_REASSIGN), purge job. |
| SC3-BE-09 | Extend audit, isolation and permission-matrix tests; SSE isolation tests. |

## 7.4 Frontend Tasks

| Task | Description |
| --- | --- |
| SC3-FE-01 | P-08 walk-in eligibility/service/doctor, P-09 details, P-10 live status; queue section on P-07. |
| SC3-FE-02 | R-02 queue board (Registered / Waiting / Called / Done per doctor, counters, pause toggle), R-05 register walk-in (incl. “Patient has no phone” with reason), R-06 check-in/find. |
| SC3-FE-03 | D-01 doctor workspace (call next, start, complete, return, no-show, unavailable today). |
| SC3-FE-04 | W-01 waiting-room display (SHOULD). |
| SC3-FE-05 | Shared SSE hook (fetch-event-source), snapshot reload, “Live / Reconnecting” indicator, aria-live announcements. |

## 7.5 Database Changes

- Migration 0004: queue_counter, queue_entry (partial unique doctor-busy index, CHECKs, status guard trigger, FK to counter), clinic_event, notification_job.

- db:verify manifest extended.

Every migration is shown as SQL and approved before it is applied (rule R-04).

## 7.6 Acceptance Tests (37)

| Test | Quality area | Level | Origin |
| --- | --- | --- | --- |
| TC-APT-012 | Appointment journey | E | SRS |
| TC-APT-013 | Appointment journey | I | SRS |
| TC-APT-024 | Doctor call/start/complete | I | SRS |
| TC-CLN-002 | Clinic opening/closing hours | I | SRS |
| TC-DOC-004 | Multi-clinic membership | I | SRS |
| TC-NFR-004 | Non-functional | I | SRS |
| TC-QUE-001 | Queue journey | E | SRS |
| TC-QUE-002 | Walk-in capacity and cutoff | I/E | SRS |
| TC-QUE-003 | Walk-in capacity and cutoff | I | SRS |
| TC-QUE-004 | Unique daily queue tokens | I | SRS |
| TC-QUE-005 | Arrival confirmation | I/E | SRS |
| TC-QUE-006 | Doctor call/start/complete | I/E | SRS |
| TC-QUE-007 | Doctor call/start/complete | I | SRS |
| TC-QUE-008 | Doctor call/start/complete | U/I | SRS |
| TC-QUE-009 | SSE permissions and reconnection | E | SRS |
| TC-QUE-010 | Doctor call/start/complete | I | SRS |
| TC-QUE-011 | Queue journey | I | SRS |
| TC-QUE-012 | Duplicate registration handling | I | SRS |
| TC-QUE-013 | Timezone and DST | I | SRS |
| TC-QUE-014 | Public access privacy | E | SRS |
| TC-QUE-015 | Queue journey | E | SRS |
| TC-QUE-016 | Queue journey | E | SRS |
| TC-QUE-017 | Queue journey | I/E | SRS |
| TC-QUE-018 | SSE permissions and reconnection | E | SRS |
| TC-QUE-019 | Walk-in capacity and cutoff | I | SRS |
| TC-QUE-020 | Walk-in capacity and cutoff | I | SRS |
| TC-QUE-021 | SSE permissions and reconnection | E | SRS |
| TC-QUE-022 | SSE permissions and reconnection | I | SRS |
| TC-QUE-023 | Doctor call/start/complete | I | SRS |
| TC-QUE-024 | Doctor call/start/complete | I | SRS |
| TC-QUE-025 | Duplicate registration handling | I | SRS |
| TC-QUE-026 | Arrival confirmation | I | SRS |
| TC-QUE-027 | Unique daily queue tokens | I | SRS |
| TC-QUE-028 | Arrival confirmation | I | SRS |
| TC-QUE-029 | Phone and name validation | I/E | SRS |
| TC-SEC-007 | SSE permissions and reconnection | I | SRS |
| TC-VAL-004 | Phone and name validation | I | SRS |

Full scenarios and expected results: ACCEPTANCE_TEST_MATRIX_v1.1.csv (filter gate = SC-3). At gate closure every earlier gate’s tests are re-run as part of the full regression.

## 7.7 Dependencies

SC-2 closed (patients, appointments, tokens, idempotency, worker entry). Business rules decided: D-02, D-03, D-12, D-14.

## 7.8 Exit Criteria

- Journey B and scheduled check-in demonstrable end to end with live updates on four screens.

- TC-QUE-003, -004, -007, -027 pass 10 consecutive runs; TC-QUE-009 p95 ≤ 2 s.

- SSE isolation (TC-SEC-007) and reconnection (TC-QUE-021/022) pass.

- Full regression SC-1..SC-3 green; gate report; stop for approval.

## 7.9 Estimated Complexity

Very high (state machines, locking, SSE fan-out, worker, 8 screens).

## 7.10 Credit-Spending Checkpoint

Budget control for SC-3 Report at $4.50. At $7.20 freeze, defer SHOULD items in this order: FR-QUE-017 display, FR-QUE-020 no-phone exception, FR-QUE-019 reassign, FR-DOC-006 unavailable-today, FR-QUE-015 leave queue, FR-CLN-007 pause. At $9.00 (planning cap) stop and ask the Product Owner (D-06). The amount is a planning cap, not a guarantee (D-06). The user records the credit balance in the ledger after closure (rule R-13).

## 7.11 Explicitly Deferred Work

- Today dashboard R-01 and reports (SC-4).

- Multi-instance SSE fan-out (post-MVP, ADR-012 already compatible).

- Estimated waiting time in minutes (SRS 18).

# 8. Gate SC-4 — Dashboards, UX and E2E (cap $6.00)

## 8.1 Objectives

- Deliver the Today dashboard, date-range reports and CSV export with metrics exactly as defined in SRS 11.5.

- Deliver audit log and patient detail screens.

- Complete the tenant-security suite across every route and stream.

- Bring every MVP screen to WCAG 2.2 AA and responsive targets.

- Deliver the Playwright E2E journeys.

## 8.2 Functional Requirements (9)

| FR | Priority | Requirement (abridged — SRS §7 is authoritative) |
| --- | --- | --- |
| FR-PAT-004 | SHOULD | Clinic Admin and Receptionist shall correct a patient’s name or phone; each change is audited with old and new values… |
| FR-PAT-005 | SHOULD | Staff shall view a patient’s operational visit history in their clinic (date, service, doctor, source, final status). |
| FR-RPT-001 | MUST | The Today dashboard (Clinic Admin, Receptionist; Doctor: own-doctor subset per Section 10) shall show, updating live:… |
| FR-RPT-002 | MUST | Clinic Admin shall view a report for a selected date range (≤ 90 days, clinic-local dates) showing completed visits by… |
| FR-RPT-003 | MUST | The report shall show waiting time (WAITING → first CALLED: median, p90, max) and consultation duration… |
| FR-RPT-004 | MUST | The report shall show counts and rates of: appointment cancellations (by patient / by staff), appointment no-shows,… |
| FR-RPT-005 | SHOULD | Clinic Admin shall export the aggregate report as CSV. Exports shall contain no patient names or phone numbers. |
| FR-RPT-006 | MUST | All report figures shall be computed in the clinic’s time zone and scoped to the requesting user’s clinic. |
| FR-AUD-004 | SHOULD | Clinic Admin shall view and filter the clinic’s audit log; Platform Administrator shall view platform-level events only. |

Non-functional requirements addressed: NFR-ACC-001..003, NFR-RESP-001..002, NFR-USE-002, NFR-COMP-001 (Chromium + WebKit smoke), NFR-PERF-005, NFR-SEC-004 (complete).

## 8.3 Backend Tasks

| Task | Description |
| --- | --- |
| SC4-BE-01 | reporting module: today snapshot (doctor own subset, C-08), summary metrics (median/p90/max), CSV without PII. |
| SC4-BE-02 | Audit query endpoints (clinic and platform). |
| SC4-BE-03 | Patient detail, visit history, correction (masked audit), anonymise (SHOULD). |
| SC4-BE-04 | Isolation suite completed for all routes and streams, including as a user with memberships in both test clinics; permission-matrix test over all 47 capabilities. |

## 8.4 Frontend Tasks

| Task | Description |
| --- | --- |
| SC4-FE-01 | R-01 Today dashboard (live), A-07 reports (lightweight charts), A-08 audit log, R-08 patient detail, PA-02 platform audit. |
| SC4-FE-02 | Accessibility pass: axe on every screen, keyboard walkthroughs, focus management, contrast, 44 px targets, 200 % zoom. |
| SC4-FE-03 | Responsive pass at 360/430/768/1280 px; empty, loading and error states everywhere. |
| SC4-FE-04 | Playwright E2E: Journey A, Journey B, check-in, doctor flow, one denial per role, live update latency. |

## 8.5 Database Changes

- No new tables. Optional read-performance indexes only if measured necessary (requires approval).

Every migration is shown as SQL and approved before it is applied (rule R-04).

## 8.6 Acceptance Tests (11)

| Test | Quality area | Level | Origin |
| --- | --- | --- | --- |
| TC-NFR-001 | Accessibility | E/M | SRS |
| TC-NFR-002 | Mobile responsiveness | E | SRS |
| TC-NFR-005 | Accessibility | E | SRS |
| TC-NFR-006 | Mobile responsiveness | M | SRS |
| TC-PAT-002 | Patient records | I | SRS |
| TC-RPT-001 | Reporting accuracy | U/I | SRS |
| TC-RPT-002 | Reporting accuracy | I | SRS |
| TC-RPT-003 | Strict tenant isolation | I | SRS |
| TC-RPT-004 | Reporting accuracy | E | SRS |
| TC-RPT-005 | Reporting accuracy | I | SRS |
| TC-RPT-006 | Reporting accuracy | I | SRS |

Full scenarios and expected results: ACCEPTANCE_TEST_MATRIX_v1.1.csv (filter gate = SC-4). At gate closure every earlier gate’s tests are re-run as part of the full regression.

## 8.7 Dependencies

SC-3 closed (queue data exists for metrics and E2E).

## 8.8 Exit Criteria

- Report figures match fixtures (TC-RPT-001/002/005/006).

- axe 0 serious/critical; responsive checks pass.

- Full isolation and permission suites green.

- E2E suite green on Chromium and WebKit.

- Full regression green; gate report; stop for approval.

## 8.9 Estimated Complexity

Medium.

## 8.10 Credit-Spending Checkpoint

Budget control for SC-4 Report at $3.00. At $4.80 freeze, defer: CSV export (FR-RPT-005 SHOULD), anonymise, PA-02 view (FR-AUD-004 SHOULD), FR-PAT-004/005 (SHOULD). At $6.00 (planning cap) stop and ask the Product Owner (D-06). The amount is a planning cap, not a guarantee (D-06). The user records the credit balance in the ledger after closure (rule R-13).

## 8.11 Explicitly Deferred Work

- Moderated usability test for SC-01..SC-03 (human activity, Product Owner-run with the fictional demo, IR-26).

- Advanced analytics (SRS 18).

# 9. Gate SC-5 — Release Readiness (cap $4.00)

## 9.1 Objectives

- Prove release readiness against SRS Section 17 Definition of Done.

- Add GitHub Actions CI, final Docker configuration, demo seed/reset with fictional data, screenshots, environment documentation and the portfolio README.

## 9.2 Functional Requirements (3)

| FR | Priority | Requirement (abridged — SRS §7 is authoritative) |
| --- | --- | --- |
| FR-DEM-001 | MUST | A seed command shall create at least two fictional clinics with distinct time zones, staff for every role, services,… |
| FR-DEM-002 | MUST | Fictional phone numbers shall use reserved/fictional ranges where available and names shall be obviously fictional; the… |
| FR-DEM-003 | SHOULD | A reset command shall restore the demo database to its seeded state. |

Non-functional requirements addressed: NFR-OPS-002, NFR-SEC-003, NFR-REL-004, NFR-PERF-001..003 (load test), NFR-CST-001.

## 9.3 Backend Tasks

| Task | Description |
| --- | --- |
| SC5-BE-01 | Extend the SC-1 GitHub Actions workflow: db:verify, Playwright smoke, concurrency tests ×10 on main, npm audit gate. |
| SC5-BE-02 | Docker: production-like compose (proxy example with SSE buffering disabled, api, worker, migrate one-shot); healthchecks. |
| SC5-BE-03 | Demo seed and reset scripts (FR-DEM-001..003) — run only after explicit approval. |
| SC5-BE-04 | Load-test script and one run at reference load using a separate fictional dataset in an approved, disposable test database (D-09). |
| SC5-BE-05 | Backup/restore procedure executed once on the demo database. |

## 9.4 Frontend Tasks

| Task | Description |
| --- | --- |
| SC5-FE-01 | Demo banner check; Playwright screenshot script for README (fictional data only). |
| SC5-FE-02 | Final cross-browser smoke. |

## 9.5 Database Changes

- No schema changes expected. Any fix requires a new reviewed migration.

Every migration is shown as SQL and approved before it is applied (rule R-04).

## 9.6 Acceptance Tests (2)

| Test | Quality area | Level | Origin |
| --- | --- | --- | --- |
| TC-DEM-001 | Demo data | M | SRS |
| TC-NFR-003 | Non-functional | M | SRS |

Full scenarios and expected results: ACCEPTANCE_TEST_MATRIX_v1.1.csv (filter gate = SC-5). At gate closure every earlier gate’s tests are re-run as part of the full regression.

## 9.7 Dependencies

SC-4 closed. Approval to run the demo seed and to create the disposable load-test database (D-09).

## 9.8 Exit Criteria

- SRS Section 17 DoD satisfied or exceptions signed off.

- CI green on release commit; npm audit 0 high/critical.

- README: architecture, setup ≤ 5 steps, env vars, test commands, known limitations, deferred list.

- Credit ledger shows total ≤ $35.

- Product Owner sign-off.

## 9.9 Estimated Complexity

Low–Medium.

## 9.10 Credit-Spending Checkpoint

Budget control for SC-5 Report at $2.00. At $3.20 freeze: reduce screenshot set and skip optional polish. At $4.00 (planning cap) stop and ask the Product Owner (D-06). The amount is a planning cap, not a guarantee (D-06). The user records the credit balance in the ledger after closure (rule R-13).

## 9.11 Explicitly Deferred Work

- Live hosting/deployment — needs separate approval (D-10); the release is a local Docker release.

- All SRS Section 18 features.

# 10. Quality Assurance Strategy

## 10.1 Test Levels

| Level | Tool | Runs against | When |
| --- | --- | --- | --- |
| Unit (U) | Vitest | Pure domain code: interval engine, DST, state machines, validation, metrics, reference generator | Targeted on every task; full at closure |
| Integration (I) | Vitest + PostgreSQL 16 (Docker) | Routes, repositories, transactions, constraints, triggers, middleware, jobs, SSE | Targeted on every task; full at closure |
| Concurrency | Vitest, parallel connections with a start barrier | Booking, rescheduling, tokens, capacity, transitions | At closure ×10 consecutive passes |
| E2E (E) | Playwright (Chromium; WebKit smoke in SC-4/5) | Running stack with fixture data | Per journey while building; full suite from SC-4 |
| Manual / tool (M) | Lighthouse, screen reader, QR scan, load tool | Built app | SC-4, SC-5 |

## 10.2 Test Environments and Data

- Separate test database; each integration test file runs in its own schema or truncates its tables; fixtures created by factories, never by the demo seed (IR-17).

- Two fixture clinics: Asia/Bangkok (no DST) and Europe/London (DST) to cover time-zone conversion and DST (TC-SCH-001…003, TC-QUE-013, TC-RPT-005).

- Injectable clock fixes “now” for time-dependent rules (NFR-TST-003).

- All names and phone numbers are fictional; phones use reserved or obviously fictional ranges.

## 10.3 Required Quality Areas and Coverage

| Quality area | Tests | How it is tested |
| --- | --- | --- |
| Strict tenant isolation | TC-RPT-003, TC-SEC-001, TC-SEC-002, TC-SEC-012, TC-SEC-017 | Route-iterating suite with two clinics; foreign IDs → 404; composite-FK rejection in SQL; reports scoped. |
| Multi-clinic membership | TC-DOC-004, TC-PLT-004, TC-STF-004, TC-STF-005 | Fixture user with memberships in two clinics and different roles: selection, switching, per-clinic permissions, removal from one clinic only, global deactivation, per-clinic doctor profiles. |
| Staff role authorization | TC-SEC-003, TC-SEC-004, TC-SEC-013, TC-SEC-014, TC-SEC-016, TC-STF-006 | Generated matrix test over all 47 capabilities × roles, run as single- and multi-clinic users; suspended read-only; DB guard triggers. |
| Public access privacy | TC-APT-009, TC-APT-022, TC-APT-023, TC-QUE-014, TC-SEC-005, TC-SEC-006, TC-SEC-011, TC-SEC-015 | Masked fields, headers, generic 404, hashes at rest, no tokens in logs, own-entry SSE payloads. |
| Phone and name validation | TC-APT-008, TC-PAT-001, TC-QUE-029, TC-VAL-001, TC-VAL-002, TC-VAL-003, TC-VAL-004 | Unit matrices for BR-030/031; strict schemas; patient matching. |
| Clinic opening/closing hours | TC-APT-003, TC-CLN-001, TC-CLN-002, TC-SCH-005, TC-SCH-006 | Interval validation, closures (full/partial/multi-day), closed weekdays, worked example SRS 12.5. |
| Doctor schedules and breaks | TC-APT-004, TC-DOC-001, TC-DOC-002, TC-DOC-003, TC-SCH-004 | Clipping to clinic hours, three breaks, exceptions, MODIFIED_HOURS. |
| Timezone and DST | TC-QUE-013, TC-SCH-001, TC-SCH-002, TC-SCH-003 | Spring-forward gap, fall-back ambiguity, UTC conversion, local midnight token reset. |
| Concurrent appointment booking | TC-APT-006, TC-APT-021 | 100 parallel holds; staff create vs public confirm. |
| Concurrent rescheduling | TC-APT-017, TC-APT-019, TC-APT-020 | Reschedule races; original preserved on failure. |
| Unique daily queue tokens | TC-QUE-004, TC-QUE-027 | 50 parallel walk-ins; mixed sources; gapless. |
| Walk-in capacity and cutoff | TC-QUE-002, TC-QUE-003, TC-QUE-019, TC-QUE-020 | Boundary times, pause, disabled, capacity boundary under concurrency, capacity release. |
| Duplicate registration handling | TC-QUE-012, TC-QUE-025 | QR duplicate rejected without disclosure; staff exception (C-02). |
| Arrival confirmation | TC-QUE-005, TC-QUE-026, TC-QUE-028 | REGISTERED excluded from line/positions/display; staff-only confirmation; cancellation from REGISTERED. |
| Doctor call/start/complete | TC-APT-024, TC-QUE-006, TC-QUE-007, TC-QUE-008, TC-QUE-010, TC-QUE-023, TC-QUE-024 | Valid/invalid transitions, DOCTOR_BUSY, double call, recall limit, reassignment race, appointment cascade. |
| SSE permissions and reconnection | TC-QUE-009, TC-QUE-018, TC-QUE-021, TC-QUE-022, TC-SEC-007 | Latency, cross-clinic isolation, display content, reconnect with snapshot, credential revocation. |
| Reporting accuracy | TC-RPT-001, TC-RPT-002, TC-RPT-004, TC-RPT-005, TC-RPT-006 | Hand-calculated fixtures, DST buckets, SRS 11.5 definitions. |
| Accessibility | TC-NFR-001, TC-NFR-005 | axe on every screen, keyboard walkthroughs, aria-live announcements. |
| Mobile responsiveness | TC-NFR-002, TC-NFR-006 | Breakpoints 360/430/768/1280 px; Lighthouse mobile; touch targets; zoom. |

## 10.4 Key Test Designs

- Concurrency harness: N independent database connections wait on a shared barrier, fire simultaneously and assert exact success/failure counts plus final table state. Run 10 consecutive times at closure; any flake is a High defect.

- Isolation harness: iterates the API inventory; for each tenant route performs the call as clinic A with clinic B’s resource IDs; expects 404 and no data in the body. Extended every gate (IR-15).

- Permission matrix test: generated from PERMISSION_MATRIX_v1.1.csv so the CSV, middleware and tests cannot drift (TC-SEC-016).

- State-machine tests: table-driven over AT-01…11 and QT-01…14 (domain) plus raw-SQL guard-trigger tests (TC-SEC-014).

- SSE tests: in-process client subscribes, the test performs a transition, asserts payload and audience; reconnection simulated by aborting the stream.

- Accessibility/responsive: Playwright with axe-core and viewport matrix; Lighthouse mobile run for public screens.

## 10.5 State-Transition Coverage

| Transition | Tests |
| --- | --- |
| AT-01 — → PENDING | TC-APT-005, TC-APT-006 |
| AT-02 PENDING → CONFIRMED | TC-APT-009, TC-APT-010 |
| AT-03 PENDING → EXPIRED | TC-APT-005 |
| AT-04 PENDING → CANCELLED | TC-APT-023 |
| AT-05 — → CONFIRMED (staff) | TC-APT-016 |
| AT-06 CONFIRMED → CONFIRMED (reschedule) | TC-APT-017, TC-APT-019, TC-APT-020 |
| AT-07 CONFIRMED → CANCELLED | TC-APT-011 |
| AT-08 CONFIRMED → CHECKED_IN | TC-APT-012 |
| AT-09 CONFIRMED → NO_SHOW | TC-APT-013 |
| AT-10 CHECKED_IN → COMPLETED | TC-APT-024 |
| AT-11 CHECKED_IN → CANCELLED | TC-APT-024 |
| QT-01 — → REGISTERED | TC-QUE-001 |
| QT-02 — → WAITING | TC-QUE-016, TC-APT-012 |
| QT-03 REGISTERED → WAITING | TC-QUE-005 |
| QT-04 REGISTERED → CANCELLED | TC-QUE-028 |
| QT-05 REGISTERED → EXPIRED | TC-QUE-011 |
| QT-06 WAITING → CALLED | TC-QUE-006, TC-QUE-007 |
| QT-07 WAITING → CANCELLED | TC-QUE-017 |
| QT-08 WAITING → WAITING (reassign) | TC-QUE-015, TC-QUE-023 |
| QT-09 CALLED → IN_CONSULTATION | TC-QUE-006 |
| QT-10 CALLED → WAITING | TC-QUE-024 |
| QT-11 CALLED → NO_SHOW | TC-APT-024 |
| QT-12 IN_CONSULTATION → COMPLETED | TC-QUE-006 |
| QT-13 WAITING/CALLED → CANCELLED (day close) | TC-QUE-011 |
| QT-14 IN_CONSULTATION → COMPLETED (auto_closed) | TC-QUE-011 |
| Any illegal transition (app) | TC-QUE-008 |
| Any illegal transition (DB trigger) | TC-SEC-014 |

## 10.6 Supplementary and Revision B Tests

The 36 supplementary tests that close the coverage gaps found in the consistency review (IR-20) are now part of SRS §16.8:

| Test | Gate | Quality area | Verifies |
| --- | --- | --- | --- |
| TC-APT-019 | SC-2 | Concurrent rescheduling | FR-APT-011 |
| TC-APT-020 | SC-2 | Concurrent rescheduling | FR-APT-005, FR-APT-011 |
| TC-APT-021 | SC-2 | Concurrent appointment booking | FR-APT-006, FR-APT-010 |
| TC-APT-022 | SC-2 | Public access privacy | FR-APT-008, NFR-PRIV-002, NFR-PRIV-003 |
| TC-APT-023 | SC-2 | Public access privacy | FR-SEC-007, BR-054 |
| TC-SCH-001 | SC-1 | Timezone and DST | FR-DOC-004, FR-CLN-003, NFR-DAT-001 |
| TC-SCH-002 | SC-1 | Timezone and DST | FR-DOC-004 |
| TC-SCH-003 | SC-1 | Timezone and DST | FR-CLN-003, NFR-DAT-001 |
| TC-SCH-004 | SC-1 | Doctor schedules and breaks | FR-DOC-002, BR-041 |
| TC-SCH-005 | SC-1 | Clinic opening/closing hours | FR-CLN-004, FR-DOC-003, BR-043, BR-046 |
| TC-SCH-006 | SC-1 | Clinic opening/closing hours | FR-CLN-003, FR-QR-004 |
| TC-VAL-001 | SC-2 | Phone and name validation | BR-030, FR-SEC-008 |
| TC-VAL-002 | SC-2 | Phone and name validation | BR-031, FR-PAT-002 |
| TC-VAL-003 | SC-1 | Phone and name validation | FR-SEC-008 |
| TC-QUE-019 | SC-3 | Walk-in capacity and cutoff | FR-QUE-001, FR-CLN-006 |
| TC-QUE-020 | SC-3 | Walk-in capacity and cutoff | FR-QUE-015, BR-062 |
| TC-QUE-021 | SC-3 | SSE permissions and reconnection | FR-QUE-013, NFR-REL-001 |
| TC-QUE-022 | SC-3 | SSE permissions and reconnection | FR-QUE-013, FR-QUE-017, FR-STF-003 |
| TC-QUE-023 | SC-3 | Doctor call/start/complete | FR-QUE-019, FR-QUE-010 |
| TC-QUE-024 | SC-3 | Doctor call/start/complete | FR-QUE-011, BR-063 |
| TC-QUE-025 | SC-3 | Duplicate registration handling | FR-QUE-006, FR-QUE-018 |
| TC-QUE-026 | SC-3 | Arrival confirmation | FR-QUE-007, FR-QUE-008, FR-QUE-017 |
| TC-QUE-027 | SC-3 | Unique daily queue tokens | FR-QUE-004, FR-APT-012 |
| TC-SEC-012 | SC-1 | Strict tenant isolation | FR-SEC-005, Rule 2 |
| TC-SEC-013 | SC-1 | Staff role authorization | FR-PLT-003 |
| TC-SEC-014 | SC-2 | Staff role authorization | Rule 12, ADR-016 |
| TC-SEC-015 | SC-2 | Public access privacy | FR-SEC-006, ADR-011 |
| TC-SEC-016 | SC-1 | Staff role authorization | FR-SEC-004, Section 10 |
| TC-RPT-005 | SC-4 | Reporting accuracy | FR-RPT-006, FR-RPT-003 |
| TC-RPT-006 | SC-4 | Reporting accuracy | FR-RPT-004 |
| TC-NFR-005 | SC-4 | Accessibility | NFR-ACC-002 |
| TC-NFR-006 | SC-4 | Mobile responsiveness | NFR-PERF-005, NFR-ACC-003 |
| TC-NFR-007 | SC-1 | Database integrity | ADR-019, FR-AUD-003 |
| TC-APT-024 | SC-3 | Doctor call/start/complete | FR-QUE-010, FR-QUE-011, FR-APT-012 |
| TC-QUE-028 | SC-3 | Arrival confirmation | FR-QUE-011, FR-QUE-015 |
| TC-VAL-004 | SC-3 | Phone and name validation | FR-QUE-003, FR-APT-006, BR-037 |

Revision B added 7 tests for the multi-clinic membership model and the phone rules, including users who belong to two clinics and users removed from only one clinic:

| Test | Gate | Quality area | Verifies |
| --- | --- | --- | --- |
| TC-DOC-004 | SC-3 | Multi-clinic membership | FR-DOC-001, FR-QUE-009 |
| TC-PLT-004 | SC-1 | Multi-clinic membership | FR-PLT-006, BR-083 |
| TC-QUE-029 | SC-3 | Phone and name validation | FR-QUE-020 |
| TC-SEC-017 | SC-1 | Strict tenant isolation | FR-SEC-012, FR-SEC-005 |
| TC-STF-004 | SC-1 | Multi-clinic membership | FR-STF-007, FR-STF-001, FR-SEC-002, FR-SEC-005 |
| TC-STF-005 | SC-1 | Multi-clinic membership | FR-STF-003, FR-STF-007 |
| TC-STF-006 | SC-1 | Staff role authorization | FR-STF-005, BR-084 |

## 10.7 Regression and Defect Policy

| Topic | Policy |
| --- | --- |
| During development | Targeted tests for touched modules only (rule R-07). |
| Gate closure | Full unit + integration suite for all gates so far; concurrency ×10; db:verify; lint; type-check; E2E for journeys present (full E2E from SC-4). |
| Release (SC-5) | Full regression in CI on the release commit; Playwright Chromium + WebKit smoke; load test once. |
| Severity | Critical: data leak, cross-tenant access, double booking, duplicate token. High: wrong state, failed MUST test, flaky concurrency. Medium: SHOULD failure, UI defect with workaround. Low: cosmetic. |
| Gate exit | No open Critical/High; Medium documented in the gate report. |
| Flaky tests | Not allowed to be skipped; quarantined only with Product Owner approval and an IR entry. |

# 11. Traceability Summary

TRACEABILITY_MATRIX_v1.1.md maps every functional requirement to its owning gate, entities, endpoints, screens, tests and acceptance criterion. Totals:

| Measure | Result |
| --- | --- |
| Functional requirements mapped to a gate or deferral | 106 / 106 (all 102 original requirements retained with unchanged IDs; 4 added) |
| In-scope FRs with at least one test | 105 / 105 |
| Fully deferred FRs | 1 (FR-QR-006, COULD) |
| Partially deferred FRs | 4 (COULD/SHOULD parts of FR-CLN-001, FR-CLN-006, FR-QR-002, FR-APT-007) |
| NFRs with gate and verification method | 36 / 36 |
| State transitions with tests | 25 / 25 |
| Required quality areas with tests (incl. multi-clinic membership) | 19 / 19 |
| Acceptance tests | 118 (75 original + 36 supplementary + 7 new in rev B) |

## 11.1 Non-Functional Requirements by Gate

| NFR | Category | Gate | Verification |
| --- | --- | --- | --- |
| NFR-PERF-001 | Performance | SC-5 | TC-NFR-003 |
| NFR-PERF-002 | Performance | SC-2 | TC-NFR-003 |
| NFR-PERF-003 | Performance | SC-5 | TC-NFR-003 |
| NFR-PERF-004 | Real time | SC-3 | TC-QUE-009 |
| NFR-PERF-005 | Front end | SC-4 | TC-NFR-006 |
| NFR-PERF-006 | Scalability | SC-3 | TC-NFR-003 |
| NFR-REL-001 | Reliability | SC-3 | TC-QUE-021 |
| NFR-REL-002 | Reliability | SC-3 | TC-NFR-004 |
| NFR-REL-003 | Reliability | SC-2 | TC-APT-005 |
| NFR-REL-004 | Recoverability | SC-5 | SC-5 drill record |
| NFR-AVL-001 | Availability | Only if live hosting is approved (D-10); health endpoints SC-1 | /healthz, /readyz checks |
| NFR-SEC-001 | Security | Deployed part only if hosting approved (D-10) | Header check (deployed) |
| NFR-SEC-002 | Security | SC-1 | TC-APT-022 + header test |
| NFR-SEC-003 | Security | SC-5 | CI audit step |
| NFR-SEC-004 | Security | SC-1 → SC-4 | TC-SEC-001 |
| NFR-PRIV-001 | Privacy | SC-2 | Schema review + TC-SEC-015 |
| NFR-PRIV-002 | Privacy | SC-2 | TC-QUE-014, TC-APT-022 |
| NFR-PRIV-003 | Privacy | SC-2 | TC-APT-022 |
| NFR-USE-001 | Usability | Product Owner-run after SC-4 (IR-26) | Moderated test (SC-01..03) |
| NFR-USE-002 | Usability | SC-4 | Content review |
| NFR-ACC-001 | Accessibility | SC-4 | TC-NFR-001 |
| NFR-ACC-002 | Accessibility | SC-3 → SC-4 | TC-NFR-005 |
| NFR-ACC-003 | Accessibility | SC-4 | TC-NFR-006 |
| NFR-RESP-001 | Responsive | SC-2 → SC-4 | TC-NFR-002 |
| NFR-RESP-002 | Responsive | SC-4 | TC-NFR-002 |
| NFR-COMP-001 | Compatibility | SC-4 → SC-5 | E2E smoke matrix |
| NFR-MNT-001 | Maintainability | SC-1 | Lint boundary rule |
| NFR-MNT-002 | Maintainability | SC-1 | CI type-check |
| NFR-TST-001 | Testability | SC-1 → SC-3 | Coverage report |
| NFR-TST-002 | Testability | SC-4 | Playwright suite |
| NFR-TST-003 | Testability | SC-1 | Clock injection review |
| NFR-OPS-001 | Operability | SC-1 | Log format check, TC-SEC-011 |
| NFR-OPS-002 | Portability | SC-5 | Clean-machine README run |
| NFR-DAT-001 | Data | SC-1 | Schema review, TC-SCH-003 |
| NFR-I18N-001 | Internationalisation | SC-1 | String externalisation check |
| NFR-CST-001 | Cost | Every gate (ledger) | Credit ledger |

# 12. Consistency Review and Decision Status

Revision B re-ran the cross-check SRS → Architecture → ERD → Workflows → Permissions → Traceability → Gates → Tests after the Product Owner baseline review. All 29 original register items and the 7 new revision B items are decided (INCONSISTENCY_REGISTER_v1.1.md). Decisions that shape this plan:

| Decision | Effect on the plan |
| --- | --- |
| D-01 Multi-clinic membership | SC-1 builds global accounts, per-clinic memberships, clinic selection/switching and per-request re-validation; tests TC-STF-004…006, TC-PLT-004, TC-SEC-017 (SC-1), TC-DOC-004 (SC-3). |
| D-06 Planning caps | Gate amounts are planning caps; 100 % → stop and ask; USD 35 total retained. |
| D-07 Protect the core | SC-1 freeze list defers optional features, never the tenant/membership model. |
| D-08 CI from SC-1 | Minimal GitHub Actions workflow in SC-1; extended in SC-5. |
| D-09 Load testing | Separate fictional dataset in an approved, disposable database (SC-5). |
| D-10 Local release | SC-5 delivers a local Docker release; hosting needs separate approval. |
| D-11 No CAPTCHA / RLS | No tasks for either; residual risks documented in SRS 14.2. |
| D-12 Phone rule | Public forms never bypass phone (TC-VAL-004); FR-QUE-020 staff exception in SC-3 (SHOULD). |
| D-02, D-03, D-04, D-05, D-14 | Notification, duplicate-check, idempotency, COULD-deferral and business-default decisions are implemented as written in the SRS. |

# 13. Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| SC-1 overruns its $7 cap (broadest scope). | High | High | Freeze list at 80 %; reusable components; scheduling engine kept pure and small. |
| Concurrency tests flaky in cloud sessions. | Medium | High | Barrier-based harness; database-level guarantees; ×10 runs only at closure. |
| Prisma drops hand-written constraints on later migrations. | Medium | High | db:verify manifest after every migration (TC-NFR-007); review generated SQL (R-04). |
| SSE behaves differently behind proxies. | Medium | Medium | X-Accel-Buffering: no, heartbeat; Vite proxy configured; production proxy example in SC-5. |
| Time-zone/DST defects in availability or reports. | Medium | High | Two fixture time zones; DST tests in SC-1 and SC-4. |
| Repeated context reading consumes credits. | High | Medium | CLAUDE.md summary; gate rows only; rules R-02 and R-10. |
| Open business decisions change behaviour late. | Medium | Medium | Defaults isolated in one function or setting each (IR-23). |
| No contingency in the $35 total. | High | High | Planning caps with stop-and-ask at 100 % (D-06); ordered SHOULD deferral lists; Product Owner approval for reallocation. |
| Multi-clinic identity adds SC-1 scope. | Medium | High | Small design (session columns + one endpoint); optional SC-1 features deferred first (D-07). |

# 14. Next Step

Next step Freeze Baseline v1.1 (revision B). No register item blocks the freeze. Development does not start, and no Claude Code Cloud credits are used, until the Product Owner separately approves the SC-1 kickoff.